# Zendesk to ServiceNow/Salesforce Migration Phase Plan

This plan outlines the end-to-end migration approach for replicating Zendesk capabilities into ServiceNow and Salesforce. It defines migration phases, key activities, dependencies, and responsible teams.

## Phase 1 – Discovery & Assessment

Objective: Collect all Zendesk configuration and integration details for replication feasibility.

Duration: 2–3 weeks

Key Activities:

Conduct discovery sessions using the Zendesk questionnaire.

Export triggers, automations, SLAs, macros, and ticket forms.

Document integrations (Opsgenie, Teams, Jira, Telephony).

Assess capability feasibility in ServiceNow and Salesforce.

Identify process and data dependencies between Care and Support teams.

Key Roles: Zendesk Admin, ServiceNow Architect, Salesforce Solution Designer, Business Analyst

## Phase 2 – Design & Solution Mapping

Objective: Map Zendesk configurations to ServiceNow and Salesforce equivalents.

Duration: 2 weeks

Key Activities:

Design data model and workflow mapping documents.

Define integration patterns (Opsgenie, Teams, Jira).

Map SLAs and routing rules to Flow Designer and Omni-Channel.

Create configuration design and review with stakeholders.

Key Roles: Solution Architects, Integration Engineer, Business Analyst

## Phase 3 – Build & Configuration

Objective: Configure features, integrations, and automation in both target platforms.

Duration: 4–6 weeks

Key Activities:

Set up inbound email actions, ticket forms, and routing logic.

Configure automations, SLAs, macros, and notifications.

Implement Help Center, knowledge base, and chat widget.

Integrate Opsgenie, Teams, and Jira via APIs or connectors.

Key Roles: Platform Admins, Integration Developers, QA Lead

## Phase 4 – Testing & Validation

Objective: Ensure full functionality, accuracy, and parity with Zendesk workflows.

Duration: 2–3 weeks

Key Activities:

Conduct UAT for all Care/Support workflows.

Validate SLAs, routing, and ticket automation behavior.

Test Opsgenie, Teams, and Jira integrations end-to-end.

Perform regression and data validation testing.

Key Roles: QA Team, Business SMEs, Admins

## Phase 5 – Training & Go-Live Readiness

Objective: Prepare end users and support teams for production transition.

Duration: 1–2 weeks

Key Activities:

Deliver user and admin training sessions.

Prepare SOPs, KB articles, and support handbooks.

Set up dashboards for monitoring SLAs and ticket queues.

Plan Zendesk freeze and migration cutover activities.

Key Roles: Change Manager, Trainers, Platform Admins

## Phase 6 – Go-Live & Hypercare

Objective: Execute final cutover and monitor system performance post-launch.

Duration: 2 weeks

Key Activities:

Migrate Zendesk data (tickets, forms, users).

Validate integration syncs and workflow triggers.

Run daily monitoring and issue triage sessions.

Stabilize operations and close open defects.

Key Roles: Project Manager, Support Engineers, Platform Admins

## Dependencies & Risk Considerations

• Access to Zendesk admin configuration and API endpoints.
• Integration API keys and credentials for Opsgenie, Teams, and Jira.
• Sandbox readiness for ServiceNow and Salesforce.
• Sign-off from Care and Support leads on SLA rules.
• Business team availability during UAT and go-live.

## Overall Migration Timeline

Estimated Total Duration: 12–16 weeks

1. Discovery & Assessment – 2–3 weeks
2. Design & Mapping – 2 weeks
3. Build & Configuration – 4–6 weeks
4. Testing & Validation – 2–3 weeks
5. Training & Go-Live – 1–2 weeks
6. Hypercare – 2 weeks